74-1.003 Initiation.

(1) Project Initiation is the first phase in the project management lifecycle. In the Initiation phase, information technology projects are transitioned from ideas to a viable project proposal (through the Agency’s project request process) for consideration and approval by the Agency’s management.

(2) The Agency must complete the Pre-Charter Risk and Complexity (R&C) Assessment for the project (see Rule 74-1.002 ‒ Risk and Complexity Assessment, F.A.C.). This assessment will provide the project risk and complexity levels and resulting R&C Category, which will define the management control activities required for the Initiation phase.

(3) The following matrix lists Initation phase activities and documents required for the project based on its R&C Category as determined by the Pre-Charter R&C Assessment.

(4) If an individual document listed in the matrix below is not required for a given R&C Category, the Agency is still expected to conduct the planning activity and summarize the results in the Project Charter.

(5) Specific document templates are not prescribed – any project documentation that contains the information specified in the requirements below is acceptable.

| INITIATION PHASE |  | Risk & Complexity Category |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Documentation or Activity | Requirements | 4 | 3 | 2 | 1 |
| Business Case and Alternative Analysis | Articulate a clear path to a return on investment (ROI) or business value in instances where a positive ROI is not present. Demonstrate a clear understanding of the processes, costs, strengths, and weaknesses of the Agency’s current business process. Document, identify, and analyze potential solutions. Provide a compelling argument for implementation and examine benefits and risks associated with the recommended course of action as well as not taking the action. | Required | Required | Preparation of a Business Case and Alternatives Analysis is not required; however, the planning in this area must be included in the Project Charter. | Preparation of a Business Case and Alternatives Analysis is not required; however, the planning in this area must be included in the Project Charter. |
| Cost Benefit Analysis | Document the economic feasibility of the alternatives being considered including the planned project costs, as well as each of the tangible benefits, and then calculate key financial performance metrics such as ROI and payback period. | Required | Required | Preparation of a Cost Benefit Analysis is not required; however, the planning in this area must be included in the Project Charter. | Preparation of a Cost Benefit Analysis is not required; however, the planning in this area must be included in the Project Charter. |
| Project Charter | Document and formally communicate the existence of the project; appoint the project manager; identify the stakeholders and the project governance framework; authorize the expenditure of resources; establish the initial budget, schedule, and scope. This will serve as the basis for detailed planning. | Required | Required | Required | Required |
| Centralized Project Repository | Establish a centralized project repository to house and archive all project documentation. This repository should be documented in project planning materials. | Required | Required | Required | Required |
| Project Manager | The Project Manager must be PMP® certified. | Required | Required | Not Required | Not Required |
| Risk Manager | Appointment of a Risk Manager, other than the Project Manager. | Recommended | Not Required | Not Required | Not Required |
| Independent Verification and Validation (IV&V) | Employ Independent Verification and Validation (IV&V). | Recommended | Recommended | Not Required | Not Required |

(6) The Agency must complete the Initiation Gate R&C Assessment (see Rule 74-1.002, F.A.C. ‒ Risk and Complexity Assessment). This Assessment will confirm or adjust the project’s risk and complexity levels and the resulting R&C Category, validate Initiation management control requirements, and set management control requirements for the subsequent Planning phase.

Rulemaking Authority 282.0051(18) FS. Law Implemented 282.0041, 282.0051 FS. History‒New 7-16-15.