74-1.004 Planning.

(1) In the Planning phase, the Agency develops and approves detailed project planning documents.

(2) The following matrix lists planning activities and documents required for the project based on the project’s Risk and Complexity (R&C) Category.

(a) Specific document templates are not prescribed – any project documentation that contains the information specified in the requirements below is acceptable.

(b) This documentation, whether created separately or combined as a single document, constitutes the Project Management Plan, https://www.flrules.org/Gateway/reference.asp?No=Ref-05563.

(3) If an individual document listed in the matrix below is not required for a given R&C Category, the Agency is still expected to conduct the planning activity and summarize the results in the Project Plan Summary.

| PLANNING PHASE |  | Risk & Complexity Category |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Documentation or Activity | Requirements | 4 | 3 | 2 | 1 |
| Project Scope and Objectives | Clearly delineate the project scope, specifically what is in scope and what is out of scope. Include objectives, deliverables, assumptions, and constraints. This will determine scope baselines and variances. Discuss how the project scope and objectives trace back through the Project Charter to initial project documents such as the Schedule IV-B. | Required | Required | Required | Preparation of a formal Scope and Objectives document is not required; however, the Agency must include a summary of planning in this area in the Project Plan Summary. |
| Work Breakdown Structure (WBS) | The hierarchical and incremental decomposition of the project into phases, deliverables, and work packages. Identifies all the tasks required to deliver the total scope of work to produce each deliverable. Tasks must be decomposed into subtasks until they can be estimated, observed, and evaluated. | Required | Recommended | Not Required | Not Required |
| Project Organizational and Governance Structure | A representation of the project from an organizational perspective. Include an organization chart with stakeholder and governance structures identified. Include a detailed description of the project and the Agency’s governance process with roles, responsibilities, and approval authorities identified for project documents or artifacts, including any processes for final product acceptance. Include reporting and escalation parameters for variances in schedule, cost, and scope. | Required | Required | Preparation of an Organizational & Governance Structure document is not required; however, the Agency must include a summary of planning in this area in the Project Plan Summary. | Preparation of an Organizational & Governance Structure document is not required; however, the Agency must include a summary of planning in this area in the Project Plan Summary. |
| Resource Plan | Document the resources required to complete the project and how these resources will be acquired. For personnel – identify project roles, skills, number, and resource type required, and specify the method(s) for acquiring new personnel or incorporating and backfilling the current responsibilities of existing personnel. For equipment or materials ‒ identify types, quantities, and purpose, and specify the method(s) for acquiring equipment or materials. | Required | Required | Preparation of a Resource Plan document is not required; however, the Agency must include a summary of planning in this area in the Project Plan Summary. | Preparation of a Resource Plan document is not required; however, the Agency must include a summary of planning in this area in the Project Plan Summary. |
| Project Schedule | Develop and maintain a schedule that is: fully task, resource, and cost loaded; identifies the total scope of work; base-lined and updated with project progress; and contains the information necessary to provide earned value analysis and support schedule and cost performance index (SPI and CPI) variance analysis and reporting. The Project Schedule must be updated and the Agency must track and report schedule status in their Project Status Report (see Rule 74-1.006, F.A.C. ‒ Monitoring and Controlling for status report requirements and a detailed description of SPI and CPI). | Required The Agency will update the schedule weekly. | Required The Agency will update the schedule weekly. | Develop, baseline and maintain a schedule that identifies the total scope of work, assigned resources, and task completion dates. The schedule must be updated weekly. The Agency must track and report schedule status in their Project Status Report (See Rule 74-1.006, F.A.C. ‒ Monitoring and Controlling for status report requirements). | Develop, baseline and maintain a schedule that identifies the total scope of work, assigned resources, and task completion dates. The schedule must be updated bi-weekly. The Agency must track and report schedule status in their Project Status Report (See Rule 74-1.006, F.A.C. ‒ Monitoring and Controlling for status report requirements.). |
| Project Budget | Develop and maintain a Project Budget, which must include specific fiscal year cost totals over the life of the project and the overall total cost of the project. Also include a description of the funding source(s) for the Project and a breakdown of the Project costs by major expense categories. | Required | Required | Required | Required |
| Project Spending Plan | Develop and maintain a Project Spending Plan, which, as a component of the Project Budget, must include monthly budgeted and actual costs for Other Personal Services (OPS) staff, contractors, deliverables, major project tasks, hardware, Commercial off-the-shelf (COTS) software, miscellaneous equipment, and other costs for each fiscal year. | Required | Required | Preparation of a Project Spending Plan is not required; however, the Agency must include summary spending plan information in the Project Plan Summary with detail required for the Project Status Report (See Rule 74-1.006, F.A.C. ‒ Monitoring and Controlling for detailed requirements for the project status report). | Preparation of a Project Spending Plan is not required; however, the Agency must include summary spending plan information in the Project Plan Summary with detail required for the Project Status Report (See Rule 74-1.006, F.A.C. ‒ Monitoring and Controlling for detailed requirements for the project status report). |
| Communications Plan | Identify the project information requirements of stakeholders and detail what, when, and how information will be collected and reported. This will include the responsibility, frequency, format, and distribution method for meeting summaries, project status reports, project governance meetings, and stakeholder communications, including reporting variances in schedule, cost, or scope and emerging risks or issues. Include documentation for Decision Tracking and Action Item Tracking (see Rule 74-1.006, F.A.C. ‒ Monitoring and Controlling). | Required | Required | Required | Preparation of a Communication Plan is not required; however, the Agency must include a summary of planning in this area in the Project Plan Summary. |
| Change Management Plan | Document the change control process and documentation involved in identifying, escalating, approving, and managing project change requests related to the project’s schedule, cost, or scope baselines, or a change to project deliverables (see Rule 74-1.006, F.A.C. ‒ Monitoring and Controlling). Include a summary of the change governance framework (see Organizational & Governance Structure above). | Required | Required | Required | Preparation of a Change Management Plan is not required; however, the Agency must include a summary of planning in this area in the Project Plan Summary. |
| Quality Management Plan | Document the processes and procedures for ensuring quality planning, quality assurance, and quality control are all conducted. | Required | Required | Preparation of a Quality Management Plan is not required; however, the Agency must include a summary of planning in this area in the Project Plan Summary. | Preparation of a Quality Management Plan is not required; however, the Agency must include a summary of planning in this area in the Project Plan Summary. |
| Deliverable Acceptance Plan | Document each deliverable, the acceptance criteria for each deliverable, and the deliverable acceptance process. | Required | Required | Required | Preparation of a Deliverable Acceptance Plan is not required; however, the Agency must include a summary of planning in this area in the Project Plan Summary |
| Risk Management Plan | Document the process for the descriptive identification (listing), evaluation (probability and impact), prioritization, and response to risks (specified mitigation strategies for each risk), as well as the nature of any time sensitivity to risks that may impact the project. Identify the roles and responsibilities of project staff assigned to risks. Identify and document the process to be used for tracking, periodic review, and update of Risks (see Rule 74-1.006, F.A.C. ‒ Monitoring and Controlling). | Required | Required | Required | Preparation of a Risk Management Plan is not required; however, the Agency must include a summary of planning in this area in the Project Plan Summary. In addition, Agencies must track risks and report their status in the Project Status Report (See Rule 74-1.006, F.A.C. ‒ Monitoring and Controlling for detailed requirements). |
| Issue Management Plan | Document the process for (and the documentation of) the identification, evaluation, prioritization, management, and response to issues impacting the project. Identify and document the process to be used for tracking, periodic review, and update of Issues (see Rule 74-1.006, F.A.C. ‒ Monitoring and Controlling). Identify the roles and responsibilities of project staff. | Required | Required | Required | Preparation of an Issue Management Plan is not required; however, the Agency must include a summary of planning in this area in the Project Plan Summary. In addition, Agencies must track issues and report their status in the Project Status Report (See Rule 74-1.006, F.A.C. ‒ Monitoring and Controlling for detailed requirements.). |
| Procurement Management Plan | If procurement is required by the project, document any products or services needed, identify the necessary products and services to be purchased, along with the appropriate purchasing methods, rules, and statutes affecting these activities. | Required | Required | Required | Preparation of a Procurement Management Plan is not required; however, the Agency must include a summary of planning in this area in the Project Plan Summary. |
| Organizational Change Management Plan | Assess and document the impact of delivering the project’s products to the user organization and individual users; the readiness of the user organization and individual users to accept those changes; and identify, describe, and plan the action necessary to facilitate those changes. | Required | Required | Preparation of an Organizational Change Management Plan is not required; however, the Agency must include a summary of planning in this area in the Project Plan Summary. | Preparation of an Organizational Change Management Plan is not required; however, the Agency must include a summary of planning in this area in the Project Plan Summary. |
| System Security Plan | See Rule Chapter 71A-1, F.A.C. ‒ Florida Information Technology Resource Security Policies and Standards for requirements for System Security Planning. | Required | Required | Required | Required |
| Requirements Traceability Matrix (RTM) | Prepare a document (usually a table) that links high-level design and requirements with detailed requirements, detailed design, test plan, and test cases. The RTM ensures that all requirements are identified and correctly linked (from high-level to detailed and technical levels) throughout the project. | Required | Required | Required | Not Required |
| Project Plan Summary | A document providing an overview of the planning for the management of the project that addresses all of the aforementioned documents and activities. | Not Required | Not Required | Required | Required |

(4) The Agency must complete the Planning Gate R&C Assessment at the end of the Planning phase (see Rule 74-1.002 ‒ Risk and Complexity Assessment, F.A.C.). This Assessment will confirm or adjust the project’s risk and complexity levels and the resulting R&C Category, validate Planning management control requirements, and set management control requirements for the subsequent Execution and Monitoring and Controlling phases.

Rulemaking Authority 282.0051(18) FS. Law Implemented 282.0041, 282.0051 FS. History‒New 7-16-15.