74-1.006 Monitoring and Controlling.

(1) Project Monitoring and Controlling spans all phases of the project and involves the regular review of project status in order to identify variances from approved project schedule, cost, and scope.

(2) Risk and Complexity (R&C) Category 4 and 3 Projects will use Earned Value analysis to ensure that the schedule provides an accurate representation of project status.

(a) Schedule Performance Index (SPI)

1. SPI is a measure of schedule efficiency expressed as a ratio of Earned Value (EV) to Planned Value (PV): SPI = EV/PV, where Earned Value is the measure of work performed expressed in terms of the budget amount authorized for that work, and Planned Value is the authorized budget assigned to scheduled work. Planned Value corresponds to the approved baseline budget.

2. A SPI value of less than 1.0 indicates that less work was completed, in a given time frame, than was planned.

3. A SPI value greater than 1.0 indicates that more work was completed, in a given time frame, than was planned.

(b) Cost Performance Index (CPI)

1. CPI is a measure of cost efficiency of budgeted resources for the work completed. CPI is expressed as a ratio of Earned Value (EV) to Actual Cost (AC): CPI = EV/AC, where Earned Value is the measure of work performed expressed in terms of the budget amount authorized for that work, and Actual Cost is the realized cost incurred for the work performed on an activity or set of activities during a specific time period.

2. A CPI value of less than 1.0 indicates a cost overrun for work completed, in a given time frame.

3. A CPI value greater than 1.0 indicates a cost underrun of performance to date.

(3) The following matrix details Monitoring and Controlling documentation and activities required for the project based on the project’s R&C Category.

| MONITORING AND CONTROLLING PHASE |  | Risk & Complexity Category |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Documentation or Activity | Requirements | 4 | 3 | 2 | 1 |
| Monitor and Control Project Schedule | Update the schedule to reflect actual progress toward completion of scheduled tasks, milestones, and deliverables. | The Agency will update the schedule weekly. | The Agency will update the schedule weekly. | The Agency will update the schedule weekly. | The Agency will update the schedule bi-weekly. |
|  | Use SPI to assess schedule variance. If SPI analysis indicates a trend towards a variance equal to or greater than 10% (SPI score ≤ 0.90 or ≥ 1.10), communicate the variance explanation to the project stakeholders. | Required | Required | Not Required | Not Required |
|  | Evaluate the baselined schedule against current progress. 1. Identify overdue tasks and compute the percentage of late tasks related to total tasks to date (Number of Overdue Tasks/Number of Total Tasks). 2. If this analysis indicates a trend towards a variance equal to or greater than 10%, communicate the variance explanation to the project stakeholders. | Not Required | Not Required | Required | Required |
|  | If the schedule requires revision, follow the project change control process and the governance process. | Required | Required | Required | Required |
| Monitor and Control Project Cost | Monitor project costs at least monthly to identify both positive and negative variances between planned and actual expenditures. 1. Compare planned costs to actual costs captured in the spend plan or the budget. 2. Identify the difference in planned and actual costs and compute the percentage of cost variance for the period (Cost Variance/Total Planned Cost). 3. If there is a variance (positive or negative) equal to or greater than 10%, communicate the variance explanation to the project stakeholders. | Required | Required | Required | Required |
|  | Use CPI to assess cost variance. If the CPI analysis indicates a trend towards a variance equal to or greater than 10% (CPI score ≤ 0.90 or ≥ 1.10), communicate the variance explanation to the project stakeholders. | Required | Required | Not Required | Not Required |
|  | If the budget requires revision, follow the approved project change control process and governance process. | Required | Required | Required | Required |
| Monitor and Control Project Scope | Monitor project status and product scope, and manage changes to the original and agreed-upon scope as documented in the approved project planning documents. If the scope requires revision, follow the approved project change control and governance processes. | Required | Required | Required | Required |
| Monitor and Control Project Quality | Control quality as documented in the Quality Management Plan or the Project Plan Summary. | Required | Required | Required | Required |
| Monitor and Control Project Change | Follow the change control process(es) documented in the Change Management Plan or the Project Plan Summary. Complete an Event-Driven Risk & Complexity (R&C) Assessment for significant change requests (see Rule 74-1.002, F.A.C. ‒ Risk and Complexity Assessment). This assessment will confirm or adjust the project’s cumulative risk and complexity levels and R&C Category, and assist the Agency in determining whether changes to any project management plan documents and baselines are needed. If changes to any project plans, documents, or baselines are needed, follow the approved project change control process and governance processes. When proposing substantial project change requests for governance approval, the request must include the results of the Event-Driven R&C Assessment.Maintain a Change tracking log that includes Change description, project impact (scope, schedule, and cost), owner, and status. This log is used to track, enter, review, analyze, update, monitor, and report on project changes. | Required | Required | Required | Required |
| Monitor and Control Project Procurement | If procurement is required, control procurements as documented in the approved Procurement Management Plan or the Project Plan Summary. | Required | Required | Required | Required |
| Monitor and Control Project Risks | Control risks as documented in the approved Risk Management Plan or Project Plan Summary. Perform risk reassessments to identify new risks, reassess current risks, escalate risks to issues, and close outdated risks. Maintain a risk tracking log that includes risk description, owner, response/mitigation strategy, as well as risk probability, impact (or criticality), and tolerance. This log is used to track, enter, review, analyze, update, monitor, and report on risks. | Required | Required | Required | Required |
| Monitor and Control Project Issues | Control issues as documented in the approved Issue Management Plan or Project Plan Summary. Review issues to identify new issues, reassess current issues, and close resolved issues. Maintain an issue tracking log, which includes Issue description, owner, status, and priority. This log is used to track, enter, review, analyze, update, monitor, and report on issues. | Required | Required | Required | Required |
| Decision Tracking | Maintain a decision tracking log that includes decision description, approval authority, date, project impact (scope, schedule, and cost), and status. This log is used to track, enter, review, analyze, update, monitor, and report on decisions. | Required | Required | Required | Recommended |
| Action Item Tracking | Maintain an action item log that includes Action Item description, owner, dates assigned and due, priority, and status. This log is used to track, enter, review, analyze, update, monitor, and report on action items. | Required | Required | Required | Recommended |
| Requirements Traceability Matrix (RTM) | Review and amend the RTM to capture progressive detail of requirements linkage throughout the project. This matrix is used to document and link requirements from their origin to the deliverables that satisfy them. | Required | Required | Required | Recommended |
| Lessons Learned | Capture lessons learned from project team and stakeholders throughout the project. | Required | Required | Recommended | Recommended |

(4) The Agency will report project status based on the project’s R&C Category. Form AST-F-0505B, Project Status Report (07/15), is hereby incorporated by reference in this rule. Form AST-F-0505B can be found on the AST website at: http://www.ast.myflorida.com/. Status reports will include:

| MONITORING AND CONTROLLING PHASE |  | Risk & Complexity Category |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Documentation | Requirements | 4 | 3 | 2 | 1 |
| Interim Project Status Report | Sections 1, 2, 3, and 5 of the Project Status Report Form | Bi-weekly | Bi-weekly | Recommended | Recommended |
| Monthly Project Status Report | All Sections of the Project Status Report Form | Monthly | Monthly | Monthly | Monthly |
| Sections | Items Required | 4 | 3 | 2 | 1 |
| Section 1 – Project Status Overview | A. Overview of Project Progress. | Required | Required | Required | Required |
|  | B. Schedule Performance Index (SPI) Cost Performance Index (CPI) | Required | Required | Not Required | Not Required |
|  | C. Overall Status | Required | Required | Required | Required |
| Section 2 – Project Progress | A. Project Milestones & Deliverables | Required | Required | Required | Required |
|  | B. Major Project Tasks & Activities | Required | Required | Required | Not Required |
|  | C. Reports & System Interfaces | Required | Required | Not Required | Not Required |
|  | D. Scope Changes | Required | Required | Required | Required |
| Section 3 – Project Issues and Risks | A. Project Issues | Required | Required | Required | Required |
|  | B. Project Risks | Required | Required | Required | Required |
| Section 4 – Project Spend Plan | Attach current project spend plan to Status Report | Required | Required | Not Required | Not Required |
|  | A. Major Project Costs | Required | Required | Required | Required |
|  | B. Identify Planned Cost vs. Actual Cost by Category | Required | Required | Not Required | Not Required |
| Section 5 – Project Summary | Scope Statement, Project Objectives, Benefits | Required | Required | Required | Required |

Rulemaking Authority 282.0051(18) FS. Law Implemented 282.0041, 282.0051 FS. History‒New 7-16-15.