- 62-780.900 Forms.

The forms used by the Department in the Contaminated Site Cleanup Criteria program are adopted and incorporated by reference in this rule. Each form is listed by rule number, which is also the form number, and with the subject, title, and effective date. Copies of forms may be obtained by writing to the Department of Environmental Protection, Bureau of Waste Cleanup, MS 4505, 2600 Blair Stone Road, Tallahassee, FL 32399-2400; or to the applicable local district office of the Department.

(1) Form 62-780.900(1), Initial Notice of Contamination Beyond Property Boundaries (effective date 12-27-07).

(2) Form 62-780.900(2), Free Product Removal Notification Form for Contaminated Sites (effective date 4-17- 05).

(3) Form 62-780.900(3), Chain of Custody Record (effective date 4-17-05).

(4) Form 62-780.900(4), Remedial Action Plan Summary (effective date 4-17-05).

(5) Form 62-780.900(5), Active Remediation Status Report Summary (effective date 4-17-05).

- TABLE A.

Submittals and Time Frames for PRSR

| Type of Report or Activity | PRSR Action or Submittal Time Frames |
| --- | --- |
| Notice of Initiation of Emergency Response Action or Interim Source Removal Action | Within 24 hours of initiation of the action |
| Interim Source Removal Plan | When seeking approval before implementation of an alternative product recovery method, groundwater recovery, soil treatment or disposal technique (Rule 62-780.500, F.A.C.) |
| Interim Source Removal Status Report | Within 60 days of initiating interim source removal activities and every 60 days thereafter or when the field activity is terminated, whichever occurs first |
| Interim Source Removal Report | Within 60 days of completion of interim source removal activities |
| Site Assessment Commenced | Within 60 days after a discharge is discovered |
| Site Assessment Report (SAR) | SAR submitted within 270 days of discharge or discovery |
| Risk Assessment Report (RAR) | Optional (within 60 days of SAR approval or within the scheduled approved in the Risk Assessment work plan) |
| Well Survey and Sampling Results pursuant to paragraph 62-780.600(3)(h), F.A.C. | Within 60 days of discovery of contamination beyond the property boundaries |
| No Further Action (NFA) Proposal | When the site meets the criteria for NFA (Rule 62-780.680, F.A.C.) |
| Natural Attenuation with Monitoring (NAM) Plan | When the site meets the criteria for NAM (Rule 62-780.690, F.A.C.) |
| Natural Attenuation with Monitoring (NAM) Report | Within 60 days of sample collection |
| Remedial Action Plan (RAP) | Within 90 days of approval of a SAR or RAR |
| As-Built Drawings | Within 120 days of initiating operation of active remediation system |
| Initiate Operation of Active Remediation System | Within 120 days of RAP approval |
| Remedial Action Status Report | Within 60 days of the anniversary date of initiating operation of active remediation system |
| Proposals submitted pursuant to subsection 62-780.700(15), F.A.C. | Optional during active remediation |
| Post Active Remediation Monitoring (PARM) Plan | When the site meets the criteria for NFA (Rule 62-780.680, F.A.C.) or Leveling Off (subsection 62-780.700(19), F.A.C.) |
| Post Active Remediation Monitoring (PARM) Report | Within 60 days of sample collection |
| Leveling Off Determination | Within 60 days of sample collection |
| Post Active Remediation Monitoring Plan resampling proposal (paragraph 62-780.750(4)(e), F.A.C.) | Within 60 days of sample collection |
| Site Rehabilitation Completion Report (SRCR) | Within 60 days of the final sampling event. If SRCR is not approved then submit modifications, etc. within 60 days of Department’s response |
| Pilot Study Work Plan | When seeking approval before implementation of a Pilot Study pursuant to subsection 62-780.700(2), F.A.C. |
| Combined Document (optional submittal) | Submitted within 270 days of discharge or discovery |
| Notices for Field Activities (except for Initiation of Emergency Response Action, De minimis Discharges or Interim Source Removal Action) | Notice to the Department within seven days but not less than 24 hours prior to performing field activity |
| Submittal to the Department of addenda, responses, or modification to plans or reports, pursuant to Rule 62-780.790, F.A.C. | Within 60 days of receipt of the Department’s response |
| Submittal of Form and Actual Notice required in subsection 62-780.220(2), F.A.C. | See text of rule for “Initial Notice of Contamination Beyond Property Boundaries” in subsection 62-780.220(2), F.A.C. |

Rulemaking Authority 376.30701, 276.30702 FS. Law Implemented 376.30701, 276.30702 FS. History–New 4-17-05, Amended 12-27-07.